## Lists (hidden)
Room Types | FFE Categories | Order Statuses | Approval Statuses | Delivery Statuses | Install Statuses | Priorities | Payment Statuses | Project Types | Project Statuses | Billing Methods | Yes/No | Design Statuses | Fixture Types | Finish Types | Surfaces | Vendor Types | Budget Categories | Damage Checks | Approval Types | Project Phases | Task Statuses | Task Categories | Measurement Types | Trades | Meeting Types | PO Statuses | Room Names | Vendor Names
Living Room | Sofa | Sourcing | Not Sent | Not Ordered | Not Scheduled | Low | Draft | Residential | Inquiry | Flat Fee | Yes | Not Started | Lighting | Paint | Wall | Furniture | Furniture | Not Checked | Furniture | Consultation | Not Started | Design | Room | General Contractor | Client Consultation | Not Ordered | Living Room | Article
Bedroom | Chair | Option Selected | Sent | Ordered | Scheduled | Medium | Sent | Commercial | Proposal | Hourly | No | Concept | Faucet | Wallpaper | Ceiling | Lighting | Lighting | Good Condition | Finish | Measurements | In Progress | Sourcing | Wall | Painter | Vendor Meeting | Ordered | Master Bedroom | West Elm
Kitchen | Table | Client Review | Approved | Shipped | In Progress | High | Paid | Office | Active | Percentage |  | In Progress | Sink | Flooring | Floor | Fabric | Rugs | Damaged | Layout | Concept Design | Waiting on Client | Purchasing | Window | Electrician | Site Visit | Confirmed | Kitchen | CB2
Bathroom | Bed | Approved | Revisions Requested | In Transit | Installed | Urgent | Partially Paid | Retail | On Hold | Hybrid |  | Client Review | Shower Fixture | Tile | Cabinet | Flooring | Decor | Missing Item | Color Palette | Sourcing | Waiting on Vendor | Client | Door | Plumber | Installation Meeting | In Production | Dining Room | Visual Comfort
Dining Room | Rug | Ordered | Rejected | Delivered | Punch List |  | Overdue | Hospitality | Completed |  |  | Approved | Tub | Countertop | Countertop | Tile | Artwork | Wrong Item | Budget | Client Approval | Complete | Vendor | Cabinet | Flooring Installer | Contractor Meeting | Shipped | Home Office | Schoolhouse
Entryway | Lighting | Shipped | On Hold | Delayed | Complete |  | Cancelled | Staging | Cancelled |  |  | Complete | Toilet | Backsplash | Shower Wall | Paint | Window Treatments |  | Purchase | Purchasing | Delayed | Site | Furniture Space | Tile Installer | Final Walkthrough | Delivered | Powder Room | Loloi
Office | Artwork | Delivered |  | Partial | On Hold |  | Unpaid |  |  |  |  | On Hold | Cabinet Hardware | Cabinet Finish | Backsplash | Wallpaper | Flooring |  | Vendor | Construction |  | Installation | Rug Area | Wallpaper Installer |  | Delayed |  | Wolf / Sub-Zero
Nursery | Mirror | Installed |  | Cancelled | [8 empty] | Door Hardware | Fabric | Upholstery | Decor | Paint/Wallcovering |  | Design Concept | Delivery |  | Admin | Lighting Location | Carpenter |  | Cancelled |  | Rejuvenation
Outdoor | Window Treatment | Cancelled | [10 empty] | Appliance | Trim | Drapery | Hardware | Contractor Labor |  |  | Installation |  | Other |  | Window Treatment Installer |  | Returned |  | Four Hands
Commercial Space | Hardware | Backordered | [10 empty] | Electrical | Stone | Other | Contractor | Installation |  |  | Styling |  |  |  | Furniture Installer |  |  |  | Signature Hardware
Other | Plumbing Fixture | Not Ordered | [10 empty] | Other | Wood |  | Installer | Shipping |  |  | Final Reveal |  |  |  | Cleaner
| Appliance | Confirmed | [11 empty] | Metal |  | Workroom | Taxes |  |  | Punch List |  |  |  | Other
| Decor | In Production | [11 empty] | Other |  | Custom Furniture | Design Fee
| Textile | Delayed | [13 empty] | Other | Contingency
| Cabinetry | Returned
Flooring
Wallcovering
Other

## 01 Welcome
INTERIOR DESIGN · FF&E PROJECT TRACKER
by Novality store · Furniture, Fixtures & Equipment Management · Excel + Google Sheets
QUICK START GUIDE
Step 1 | Add client & project details | Open the Client & Project Profile tab and fill in client name, project address, budget, dates, and designer info.
Step 2 | Add rooms / areas | Go to Room List and list every room or zone in the project with budget allocations and priority.
Step 3 | Add FF&E items | Use the Master FF&E Schedule to log every furniture, fixture, and equipment item with vendor, cost, and status.
Step 4 | Track budget, orders, approvals & delivery | Update Budget Tracker, Purchase Orders, Client Approvals, and Delivery & Installation as the project progresses.
Step 5 | Use the Dashboard for overview | The Project Dashboard auto-summarizes KPIs, spend, and status so you always know where the project stands.
WHAT EACH TAB IS USED FOR
Tab | Purpose
01 Welcome | You are here — instructions and how to use this workbook
02 Dashboard | Live KPI cards, charts, and project health at a glance
03 Client Profile | Client contact, project scope, budget, and contract details
04 Room List | All rooms/areas with budget allocation and design status
05 Master FF&E | Core schedule — every FF&E item with full cost & status tracking
06 Furniture | Furniture-only focused schedule for quick reviews
07 Fixtures | Lighting, plumbing, hardware, appliances, built-ins
08 Finishes | Paint, tile, flooring, wallpaper, countertops, fabrics
09 Sourcing | Compare product options before final selection
10 Vendors | Supplier database with trade discounts and lead times
11 Budget | Category-level budget vs estimated vs actual
12 Purchase Orders | PO and order tracking with carriers and invoices
13 Delivery & Install | Delivery logistics, damage checks, and installation
14 Client Approvals | Track every decision sent to the client
15 Timeline | Phased project plan with tasks and due dates
16 To-Do List | Daily task list for the design team
17 Measurements | Room and opening measurement log
18 Contractors | Installer / trade coordination
19 Invoices | Client billing and payment tracker
20 Meeting Notes | Consultation and site meeting notes
21 Client FF&E Report | Printable client-facing FF&E summary
22 Room Budget Report | Printable room-by-room budget report
23 Vendor Order Report | Printable vendor order summary
24 Install Checklist | Printable installation checklist
25 Punch List | Printable final punch list
HOW TO ENTER DATA
• Replace sample data with your real project information — sample rows are examples only.
• Always start a new row under the last entry; do not insert columns (formulas depend on column order).
• Yellow / green / red cells are driven by conditional formatting based on status values — pick from dropdowns.
• Currency fields use accounting format. Enter numbers only (no $ signs).
• Dates should be entered as real dates (YYYY-MM-DD) so filters and overdue logic work.
• Product links can be full URLs; they become clickable in Excel and Google Sheets.
• Image Link column can hold a URL to a product photo or mood-board image.
• On the Master FF&E tab, Total Cost and Final Cost calculate automatically from Quantity, Unit Cost, Tax, Shipping, and Discount.
COLOR CODING EXPLANATION
GREEN | Complete / Approved / On budget / Good condition
YELLOW | Pending / In progress / Awaiting response
RED | Overdue / Over budget / Delayed / Damaged / Rejected
GRAY | Cancelled / On hold / Not started
TEAL HEADERS | Section labels and accent UI
NAVY HEADERS | Column headers on all schedule tabs
DROPDOWN INSTRUCTIONS
• Click any status, category, room, priority, or type cell — a dropdown arrow appears.
• Always choose from the list so Dashboard counts and conditional formatting stay accurate.
• To customize lists (e.g. add a custom room type), unhide the Lists sheet and edit the column values, then update data validation if needed.
• Common dropdowns: Room, Category, Vendor, Status, Priority, Approval, Order, Delivery, Install, Payment.
COMPATIBILITY — EXCEL + GOOGLE SHEETS
• This file is a standard .xlsx workbook. Open it in Microsoft Excel (Windows/Mac), Excel Online, LibreOffice, or upload to Google Drive and open with Google Sheets.
• Formulas, filters, freeze panes, data validation dropdowns, and charts transfer to Google Sheets.
• Conditional formatting rules are included; colors may need a quick refresh after first open in Sheets.
• Charts on the Dashboard may need slight repositioning after import into Google Sheets.
• Recommended: Excel 2016+ or current Google Sheets. Enable editing (not Protected View) to use dropdowns and filters.
SHEET PROTECTION · FORMULA LOCK
• Formula & calculated cells are LOCKED so they cannot be overwritten by accident.
• Input cells (cream / white data fields) stay editable for daily project work.
• Soft blue cells = auto-calculated formulas (locked).
• Sheet protection password: premium
• To fully unlock a sheet in Excel: Review → Unprotect Sheet → enter password.
• Do not change protection settings unless you are customizing the template structure.
• To start a new project: File → Save As → clear sample rows (keep headers) → update Client Profile.
CELL TYPE LEGEND
SOFT BLUE | Locked formula / auto-calculated value — do not edit
WARM CREAM | Editable input — type or pick from dropdown
NAVY HEADER | Column headers — locked
GOLD INPUT | Key profile fields — editable
SUPPORT / CONTACT
• Product by Novality store. Questions or customization requests: contact Novality store support.
• Tip: Keep one master blank file and duplicate it for every new client project.
• Version: Interior Design FF&E Tracker v1.1 Premium · © Novality store

## 02 Dashboard
PROJECT DASHBOARD
TOTAL PROJECT BUDGET | TOTAL ESTIMATED COST | TOTAL ACTUAL COST | REMAINING BUDGET | BUDGET USED %
ITEMS INSTALLED | OVERDUE TASKS | PENDING APPROVALS | OPEN VENDOR ORDERS | ITEMS NOT ORDERED | DELIVERED NOT INSTALLED | TOTAL ROOMS BUDGET | ROOMS OVER BUDGET | VENDORS ON FILE | OPEN INVOICES
CHART DATA & VISUAL SUMMARIES
Budget by Room
Room | Budget | Actual
Item Status Breakdown
Status | Count
Sourcing
Approved
Ordered
Shipped
Delivered
Installed
Cancelled
Category Spend
Category | Spend
Sofa
Chair
Table
Bed
Rug
Lighting
Appliance
Artwork
Hardware
Plumbing Fixture
Delivery Status
Status | Count
Not Ordered
Ordered
Shipped
Delivered
Delayed
STATUS COLOR KEY
Green = Complete / Approved / On budget
Yellow = Pending / In progress
Red = Overdue / Over budget / Delayed
Gray = Cancelled / On hold
Soft blue = Locked formula cells
© Novality store · Interior Design FF&E Tracker · All calculated fields are password-protected

## 03 Client Profile
CLIENT & PROJECT PROFILE
Project summary — update these fields first · Novality store
| CLIENT INFORMATION |  | FIELD GUIDE
| Client Name | Alexandra Chen | Gold cells are editable inputs.
| Client Email | alexandra.chen@email.com | Gray cells are labels — locked.
| Phone Number | (555) 234-8890 | Soft blue cells = locked formulas.
Use dropdowns where provided.
| PROJECT DETAILS |  | Budget feeds the Dashboard KPIs.
| Project Name | Chen Residence Refresh | Unprotect password: premium
| Project Address | 482 Maple Lane, Portland, OR 97205 | by Novality store
| Project Type | Residential
| Design Style | Modern Organic / Warm Minimalist
| Start Date | 2026-03-01
| Target Completion | 2026-09-30
| Total Budget | 85000
| Designer Name | Jordan Blake Studio
| Project Status | Active
| Scope Summary | Full FF&E package for living, primary suite, kitchen refresh, dining, powder room, and home office. Includes furniture, lighting, rugs, finishes, and installation coordination.
| Client Notes | Prefers low-VOC finishes. Dog-friendly fabrics required in living areas. Traveling Aug 1–15 — no deliveries that window.
CONTRACT & BILLING (OPTIONAL)
| Contract Signed | Yes
| Deposit Paid | Yes
| Design Package Selected | Full Service FF&E
| Billing Method | Hybrid
| Design Fee | 12000
| Hourly Rate (if applicable) | 175
| Retainer / Deposit Amount | 4000

## 04 Room List
ROOM LIST / AREA TRACKER
Organize the project by room — budgets roll up to the Dashboard · Novality store
Room Name | Room Type | Floor/Level | Square Footage | Design Status | Budget Allocation | Estimated Spend | Actual Spend | Remaining Budget | Priority Level | Notes
Living Room | Living Room | 1 | 320 | In Progress | 15000 |  |  |  | High | Primary gathering space
Master Bedroom | Bedroom | 2 | 280 | Concept | 12000 |  |  |  | High | Ensuite suite
Kitchen | Kitchen | 1 | 220 | Client Review | 25000 |  |  |  | Urgent | Full remodel
Dining Room | Dining Room | 1 | 180 | Approved | 8000 |  |  |  | Medium | Formal dining
Home Office | Office | 2 | 140 | Not Started | 5000 |  |  |  | Low | Guest office convertible
Powder Room | Bathroom | 1 | 45 | In Progress | 3500 |  |  |  | Medium | Guest bath
TOTALS

## 05 Master FF&E
MASTER FF&E SCHEDULE
Furniture, Fixtures & Equipment — the core project schedule · Novality store
Item ID | Room | Category | Item Name | Description | Quantity | Dimensions | Material | Finish | Color | Vendor | Brand | Product Link | SKU/Model | Unit Cost | Total Cost | Tax | Shipping | Discount | Final Cost | Lead Time (wks) | Order Status | Approval Status | Delivery Status | Install Status | Notes | Image Link
FFE-001 | Living Room | Sofa | Performance Sofa | 88" deep seat sofa | 1 | 88"W x 40"D x 34"H | Performance fabric | Natural oak legs | Stone | Article | Sven | https://example.com/sofa | SV-88-ST | 1899 |  | 151.92 | 150 | 0 |  | 6 | Approved | Approved | Ordered | Not Scheduled | Client favorite
FFE-002 | Living Room | Chair | Accent Lounge Chair | Swivel lounge chair | 2 | 30"W x 32"D x 32"H | Boucle | Black metal | Ivory | West Elm | Orbit | https://example.com/chair | OR-IV | 699 |  | 111.84 | 80 | 50 |  | 4 | Approved | Approved | Shipped | Scheduled
FFE-003 | Living Room | Table | Coffee Table | Marble top coffee table | 1 | 48"W x 28"D x 16"H | Marble/Brass | Brushed brass | White marble | CB2 | Vista | https://example.com/table | VS-48 | 899 |  | 71.92 | 100 | 0 |  | 5 | Ordered | Approved | Ordered | Not Scheduled
FFE-004 | Living Room | Rug | Area Rug 9x12 | Wool flatweave | 1 | 9' x 12' | Wool | Handwoven | Ivory/Taupe | Loloi | Magnolia | https://example.com/rug | MG-912 | 1299 |  | 103.92 | 75 | 100 |  | 3 | Delivered | Approved | Delivered | Installed | Pad ordered separately
FFE-005 | Living Room | Lighting | Floor Lamp | Arched brass floor lamp | 1 | 72"H | Brass/Linen | Antique brass | Brass | Rejuvenation | Arc | https://example.com/lamp | AR-72 | 449 |  | 35.92 | 40 | 0 |  | 2 | Installed | Approved | Delivered | Installed
FFE-006 | Master Bedroom | Bed | Platform Bed King | Upholstered platform bed | 1 | King | Linen | Natural | Oatmeal | Article | Ceni | https://example.com/bed | CN-K | 1499 |  | 119.92 | 200 | 0 |  | 8 | Client Review | Sent | Not Ordered | Not Scheduled | Awaiting fabric confirmation
FFE-007 | Master Bedroom | Lighting | Pendant Pair | Glass globe pendants | 2 | 10" dia | Glass/Brass | Clear glass | Brass | Schoolhouse | Globe | https://example.com/pendant | GL-10 | 279 |  | 44.64 | 50 | 0 |  | 4 | Approved | Approved | Ordered | Not Scheduled
FFE-008 | Kitchen | Appliance | Range 36" | Dual fuel range | 1 | 36"W | Stainless | Professional | SS | Wolf | DF36450 | https://example.com/range | DF36450 | 8999 |  | 719.92 | 350 | 200 |  | 12 | Ordered | Approved | In Production | Not Scheduled | Rough-in required
FFE-009 | Kitchen | Lighting | Island Pendants | Linear brass pendants x3 | 3 | 14"H | Brass/Glass | Aged brass | Brass | Visual Comfort | Bryant | https://example.com/island | BR-14 | 520 |  | 124.8 | 90 | 0 |  | 6 | Approved | Approved | Ordered | Not Scheduled
FFE-010 | Dining Room | Table | Dining Table | Oak extension table | 1 | 72-96"L x 40"W | Oak | White oak | Natural | Ethnicraft | Bok | https://example.com/dining | BK-72 | 2499 |  | 199.92 | 250 | 0 |  | 10 | Sourcing | Not Sent | Not Ordered | Not Scheduled | Comparing 3 options
FFE-011 | Dining Room | Chair | Dining Chairs | Upholstered dining chairs | 6 | 19"W x 22"D x 33"H | Performance fabric | Oak legs | Sand | Four Hands | Haiden | https://example.com/dchair | HD-SN | 349 |  | 167.52 | 120 | 100 |  | 8 | Option Selected | Not Sent | Not Ordered | Not Scheduled
FFE-012 | Powder Room | Plumbing Fixture | Vessel Sink | Stone vessel sink | 1 | 16" dia | Marble | Honed | Carrara | Signature Hardware | Vessel | https://example.com/sink | VS-16 | 389 |  | 31.12 | 45 | 0 |  | 3 | Delivered | Approved | Delivered | Scheduled
FFE-013 | Home Office | Chair | Desk Chair | Ergonomic task chair | 1 | Standard | Mesh/Leather | Black | Black | Herman Miller | Aeron | https://example.com/aeron | AE-B | 1395 |  | 111.6 | 0 | 100 |  | 2 | Sourcing | Not Sent | Not Ordered | Not Scheduled | Budget check needed
FFE-014 | Living Room | Artwork | Large Abstract Canvas | Commissioned abstract | 1 | 48" x 60" | Canvas/Oil | Gallery wrap | Multi | Local Artist | Custom | https://example.com/art | CUST-01 | 2200 |  | 0 | 75 | 0 |  | 8 | Client Review | Sent | Not Ordered | Not Scheduled | Sketch approved
FFE-015 | Kitchen | Hardware | Cabinet Pulls | Brass bar pulls 6" | 24 | 6" | Solid brass | Unlacquered | Brass | Rejuvenation | Bin | https://example.com/pulls | BN-6 | 18 |  | 34.56 | 25 | 0 |  | 2 | Approved | Approved | Ordered | Not Scheduled
TOTALS

## 06 Furniture
FURNITURE SCHEDULE
Furniture-only view — filtered from the broader FF&E program · Novality store
Room | Furniture Item | Dimensions | Quantity | Vendor | Product Link | Fabric/Material | Finish | Cost | Approval Status | Order Status | Delivery Date | Install Date | Notes
Living Room | Performance Sofa | 88"W x 40"D x 34"H | 1 | Article | https://example.com/sofa | Performance fabric | Natural oak legs | 2200.92 | Approved | Approved |  |  | Client favorite
Living Room | Accent Lounge Chair | 30"W x 32"D x 32"H | 2 | West Elm | https://example.com/chair | Boucle | Black metal | 1539.84 | Approved | Approved
Living Room | Coffee Table | 48"W x 28"D x 16"H | 1 | CB2 | https://example.com/table | Marble/Brass | Brushed brass | 1070.92 | Approved | Ordered
Living Room | Area Rug 9x12 | 9' x 12' | 1 | Loloi | https://example.com/rug | Wool | Handwoven | 1377.92 | Approved | Delivered |  |  | Pad ordered separately
Master Bedroom | Platform Bed King | King | 1 | Article | https://example.com/bed | Linen | Natural | 1818.92 | Sent | Client Review |  |  | Awaiting fabric confirmation
Dining Room | Dining Table | 72-96"L x 40"W | 1 | Ethnicraft | https://example.com/dining | Oak | White oak | 2948.92 | Not Sent | Sourcing |  |  | Comparing 3 options
Dining Room | Dining Chairs | 19"W x 22"D x 33"H | 6 | Four Hands | https://example.com/dchair | Performance fabric | Oak legs | 2281.52 | Not Sent | Option Selected
Home Office | Desk Chair | Standard | 1 | Herman Miller | https://example.com/aeron | Mesh/Leather | Black | 1406.6 | Not Sent | Sourcing |  |  | Budget check needed

## 07 Fixtures
FIXTURES SCHEDULE
Lighting, plumbing, hardware, appliances, and built-in fixtures · Novality store
Room | Fixture Type | Item Name | Finish | Size | Vendor | Model/SKU | Quantity | Unit Cost | Total Cost | Required Rough-In Date | Order Deadline | Delivery Date | Installer Notes
Living Room | Lighting | Floor Lamp | Antique brass | 72"H | Rejuvenation | AR-72 | 1 | 449
Master Bedroom | Lighting | Pendant Pair | Clear glass | 10" dia | Schoolhouse | GL-10 | 2 | 279
Kitchen | Appliance | Range 36" | Professional | 36"W | Wolf | DF36450 | 1 | 8999 |  |  |  |  | Rough-in required
Kitchen | Lighting | Island Pendants | Aged brass | 14"H | Visual Comfort | BR-14 | 3 | 520
Powder Room | Faucet | Vessel Sink | Honed | 16" dia | Signature Hardware | VS-16 | 1 | 389
Kitchen | Cabinet Hardware | Cabinet Pulls | Unlacquered | 6" | Rejuvenation | BN-6 | 24 | 18

## 08 Finishes
FINISHES SCHEDULE
Paint, tile, flooring, wallpaper, countertops, fabrics, and more · Novality store
Room | Surface/Application | Finish Type | Product Name | Color/Finish | Material | Vendor | Product Link | SKU | Quantity Needed | Unit Cost | Total Cost | Sample Ordered | Sample Approved | Installer Notes
Living Room | Wall | Paint | Simply White OC-117 | Simply White | Latex | Benjamin Moore | https://example.com/paint | OC-117 | 5 | 65 |  | Yes | Yes | Eggshell finish
Living Room | Floor | Flooring | White Oak Engineered | Natural | White Oak | Wide Plank | https://example.com/floor | WO-7 | 320 | 12.5 |  | Yes | Yes | 7" width, matte
Kitchen | Countertop | Countertop | Calacatta Quartz | Calacatta | Quartz | Caesarstone | https://example.com/quartz | 5143 | 45 | 85 |  | Yes | Yes | Mitered island edge
Kitchen | Backsplash | Tile | Handmade Zellige | Warm White | Ceramic | Cle Tile | https://example.com/zellige | ZEL-WW | 80 | 28 |  | Yes | Pending | 2x6 vertical stack
Master Bedroom | Wall | Paint | Agreeable Gray | Agreeable Gray | Latex | Sherwin Williams | https://example.com/ag | SW 7029 | 3 | 55 |  | Yes | Yes | Flat on walls
Powder Room | Wall | Wallpaper | Grasscloth Weave | Natural Flax | Grasscloth | Phillip Jeffries | https://example.com/pj | PJ-4410 | 6 | 120 |  | Yes | Yes | Pre-pasted liner required
Kitchen | Cabinet | Cabinet Finish | Shaker Painted | Soft White | Maple | Custom Millwork |  | CM-SW | 1 | 8500 |  | No | No | Soft-close all doors
Dining Room | Drapery | Fabric | Linen Sheer | Oatmeal | Linen | Romano | https://example.com/linen | LN-OAT | 18 | 42 |  | Yes | Yes | Double width panels

## 09 Sourcing
PRODUCT SOURCING TRACKER
Compare options before locking the final FF&E selection · Novality store
Room | Item Needed | Option 1 Link | Option 1 Price | Option 2 Link | Option 2 Price | Option 3 Link | Option 3 Price | Preferred Option | Pros | Cons | Client Feedback | Final Selection
Dining Room | Dining Table | https://example.com/t1 | 2499 | https://example.com/t2 | 1899 | https://example.com/t3 | 3200 | Option 1 | Solid oak, extends | Long lead time | Likes option 1 scale
Master Bedroom | Platform Bed | https://example.com/b1 | 1499 | https://example.com/b2 | 1799 | https://example.com/b3 | 1299 | Option 1 | Performance fabric | Only 2 finishes | Wants oatmeal | Article Ceni King
Home Office | Desk Chair | https://example.com/c1 | 1395 | https://example.com/c2 | 850 | https://example.com/c3 | 450 | Option 2 | Good ergonomics, lower cost | Less brand prestige | Budget conscious
Living Room | Accent Chair | https://example.com/a1 | 699 | https://example.com/a2 | 899 | https://example.com/a3 | 549 | Option 1 | Swivel, boucle | Shows pet hair | Approved pair | West Elm Orbit

## 10 Vendors
VENDOR & SUPPLIER DATABASE
Trade accounts, discounts, and lead times in one place · Novality store
Vendor Name | Vendor Type | Contact Person | Email | Phone | Website | Account Number | Trade Discount % | Lead Time | Shipping Terms | Return Policy | Notes
Article | Furniture | Sales Team | trade@article.com | 888-555-0101 | https://article.com | ART-4521 | 15% | 4-8 weeks | Free over $999 | 30 days unused | Preferred furniture vendor
West Elm | Furniture | Trade Desk | trade@westelm.com | 800-555-0102 | https://westelm.com | WE-8891 | 20% | 2-6 weeks | Flat $99 | 30 days | Good for accents
CB2 | Furniture | Trade | trade@cb2.com | 800-555-0103 | https://cb2.com | CB2-3310 | 15% | 3-6 weeks | Varies | 14 days
Visual Comfort | Lighting | Rep: Jordan Lee | jordan@vc.com | 800-555-0104 | https://visualcomfort.com | VC-772 | 40% | 6-12 weeks | FOB | Special order no return | Trade pricing excellent
Schoolhouse | Lighting | Trade | trade@schoolhouse.com | 800-555-0105 | https://schoolhouse.com | SH-220 | 20% | 2-4 weeks | Free over $150 | 30 days
Loloi | Flooring | Rep: Sam Park | sam@loloi.com | 800-555-0106 | https://loloirugs.com | LO-991 | 25% | 2-4 weeks | Free over $500 | 30 days | Rug specialist
Wolf / Sub-Zero | Other | Builder Sales | builder@subzero.com | 800-555-0107 | https://subzero-wolf.com | SZ-110 | 0% | 8-16 weeks | Freight | No return installed | Appliances via dealer
Rejuvenation | Hardware | Trade | trade@rejuvenation.com | 800-555-0108 | https://rejuvenation.com | RJ-554 | 15% | 1-3 weeks | Free over $99 | 30 days | Hardware + lighting
Four Hands | Furniture | Rep: Ava Kim | ava@fourhands.com | 800-555-0109 | https://fourhands.com | FH-440 | 30% | 6-10 weeks | FOB warehouse | Special order | Showroom visit recommended
Signature Hardware | Hardware | Trade | trade@signaturehardware.com | 800-555-0110 | https://signaturehardware.com | SIG-88 | 10% | 1-3 weeks | Free over $99 | 30 days | Plumbing fixtures

## 11 Budget
BUDGET TRACKER
Category-level budget control with auto totals and variance · Novality store
Budget Category | Budgeted Amount | Estimated Amount | Actual Amount | Difference | Paid Amount | Balance Due | Payment Status | Notes
Furniture | 35000 |  |  |  | 0 |  | Unpaid
Lighting | 8000 |  |  |  | 0 |  | Unpaid
Rugs | 4000 |  |  |  | 0 |  | Unpaid
Decor | 2500 | 0 |  |  | 0 |  | Unpaid
Artwork | 3000 |  |  |  | 0 |  | Unpaid
Window Treatments | 4500 | 0 |  |  | 0 |  | Unpaid
Flooring | 9000 | 0 |  |  | 0 |  | Unpaid
Paint/Wallcovering | 2500 | 0 |  |  | 0 |  | Unpaid
Contractor Labor | 5000 | 0 |  |  | 0 |  | Unpaid
Installation | 2500 | 0 |  |  | 0 |  | Unpaid
Shipping | 1500 |  |  |  | 0 |  | Unpaid
Taxes | 4000 |  |  |  | 0 |  | Unpaid
Design Fee | 12000 |  |  |  | 3600 |  | Partially Paid
Contingency | 5000 | 0 |  |  | 0 |  | Unpaid
TOTALS
BUDGET SUMMARY
Total Budget
Total Estimated
Total Actual
Over/Under Budget
Remaining Balance Due
Total Paid
Paid vs Unpaid %

## 12 Purchase Orders
PURCHASE ORDER / ORDER TRACKER
Professional order log with tracking and payment status · Novality store
PO Number | Vendor | Room | Item | Quantity | Order Date | Expected Ship Date | Expected Delivery Date | Actual Delivery Date | Order Status | Tracking Number | Carrier | Invoice Number | Amount | Paid Status | Notes
PO-1001 | Article | Living Room | Performance Sofa | 1 | 2026-04-02 | 2026-05-15 | 2026-05-22 |  | Ordered |  | Freight | INV-pending | 2040.92 | Unpaid
PO-1002 | West Elm | Living Room | Accent Lounge Chairs x2 | 2 | 2026-04-05 | 2026-04-28 | 2026-05-05 |  | Shipped | 1Z999AA10123456784 | UPS | INV-WE-8891 | 1459.84 | Paid
PO-1003 | Loloi | Living Room | Area Rug 9x12 | 1 | 2026-03-20 | 2026-04-05 | 2026-04-10 | 2026-04-09 | Delivered | 1Z999BB | FedEx | INV-LO-220 | 1377.92 | Paid | Pad separate
PO-1004 | Wolf / Sub-Zero | Kitchen | Range 36" | 1 | 2026-03-15 | 2026-06-01 | 2026-06-10 |  | In Production |  | Freight |  | 9858.92 | Partially Paid | Deposit paid
PO-1005 | Visual Comfort | Kitchen | Island Pendants x3 | 3 | 2026-04-10 | 2026-05-20 | 2026-05-28 |  | Confirmed |  | UPS |  | 1775.28 | Unpaid
PO-1006 | Rejuvenation | Kitchen | Cabinet Pulls x24 | 24 | 2026-04-12 | 2026-04-25 | 2026-04-28 |  | Ordered |  | USPS |  | 491.56 | Unpaid
PO-1007 | Schoolhouse | Master Bedroom | Pendant Pair | 2 | 2026-04-08 | 2026-05-01 | 2026-05-08 |  | Ordered |  | UPS |  | 652.64 | Unpaid

## 13 Delivery & Install
DELIVERY & INSTALLATION TRACKER
Keep every delivery and install coordinated and documented · Novality store
Item | Room | Vendor | Delivery Address | Expected Delivery Date | Actual Delivery Date | Delivery Status | Received By | Damage Check | Damage Notes | Storage Location | Install Date | Installer | Installation Status | Punch List Notes
Area Rug 9x12 | Living Room | Loloi | 482 Maple Lane, Portland, OR | 2026-04-10 | 2026-04-09 | Delivered | J. Blake | Good Condition |  | On site living | 2026-04-11 | Studio Team | Installed
Accent Lounge Chairs | Living Room | West Elm | 482 Maple Lane, Portland, OR | 2026-05-05 |  | Shipped |  | Not Checked |  | TBD | 2026-05-12 | Studio Team | Scheduled
Performance Sofa | Living Room | Article | 482 Maple Lane, Portland, OR | 2026-05-22 |  | Ordered |  | Not Checked |  | TBD | 2026-05-25 | Article White Glove | Not Scheduled | Need elevator reservation
Vessel Sink | Powder Room | Signature Hardware | 482 Maple Lane, Portland, OR | 2026-04-15 | 2026-04-14 | Delivered | GC Lead | Good Condition |  | GC locked storage | 2026-05-01 | Plumber | Scheduled
Range 36" | Kitchen | Wolf / Sub-Zero | 482 Maple Lane, Portland, OR | 2026-06-10 |  | Ordered |  | Not Checked |  | Dealer warehouse | 2026-06-15 | Appliance Installer | Not Scheduled | Confirm gas rough-in
Floor Lamp | Living Room | Rejuvenation | 482 Maple Lane, Portland, OR | 2026-04-01 | 2026-03-30 | Delivered | J. Blake | Good Condition |  | On site | 2026-04-02 | Studio Team | Installed

## 14 Client Approvals
CLIENT APPROVAL TRACKER
Every design decision and purchase sign-off in one place · Novality store
Item/Design Decision | Room | Approval Type | Sent to Client Date | Client Response Date | Status | Approved Option | Client Comments | Revision Needed | Final Approval Date
Living room seating package | Living Room | Furniture | 2026-03-18 | 2026-03-22 | Approved | Article sofa + WE chairs | Love the stone fabric | No | 2026-03-22
Living room rug | Living Room | Furniture | 2026-03-10 | 2026-03-12 | Approved | Loloi Magnolia 9x12 |  | No | 2026-03-12
Kitchen range selection | Kitchen | Purchase | 2026-03-05 | 2026-03-08 | Approved | Wolf DF36450 | Proceed with stainless | No | 2026-03-08
Primary bedroom bed | Master Bedroom | Furniture | 2026-04-01 |  | Sent |  | Waiting on fabric sample photos | Yes
Dining table options | Dining Room | Furniture | 2026-04-05 |  | Sent |  | Comparing 3 options in Sourcing tab | Yes
Overall color palette | Living Room | Color Palette | 2026-02-20 | 2026-02-25 | Approved | Warm neutrals + brass | Approved board v2 | No | 2026-02-25
Powder room wallpaper | Powder Room | Finish | 2026-03-28 | 2026-04-02 | Approved | Phillip Jeffries grasscloth |  | No | 2026-04-02
Project budget confirmation | — | Budget | 2026-02-15 | 2026-02-18 | Approved | $85,000 total | OK with contingency | No | 2026-02-18
Concept presentation | — | Design Concept | 2026-02-10 | 2026-02-14 | Approved | Modern Organic concept | Minor layout tweaks only | No | 2026-02-14

## 15 Timeline
PROJECT TIMELINE / GANTT TRACKER
Phased plan with a simple week-by-week Gantt view (mark cells with X) · Novality store
Phase | Task | Assigned To | Start Date | Due Date | Completion Date | Status | Priority | Dependencies | Notes | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
Consultation | Kickoff meeting & questionnaire | Jordan Blake | 2026-03-01 | 2026-03-03 | 2026-03-03 | Complete | High |  |  | █ | █
Measurements | Site measure all rooms | Studio Team | 2026-03-05 | 2026-03-07 | 2026-03-07 | Complete | High | Kickoff |  |  | █
Concept Design | Mood boards & space plans | Jordan Blake | 2026-03-08 | 2026-03-20 | 2026-03-18 | Complete | High | Measurements |  |  | █ | █ | █
Client Approval | Concept presentation | Jordan Blake | 2026-03-20 | 2026-03-25 | 2026-03-22 | Complete | Urgent | Concept Design |  |  |  |  | █
Sourcing | Source living room package | Studio Team | 2026-03-25 | 2026-04-15 |  | In Progress | High | Concept approval |  |  |  |  | █ | █ | █
Sourcing | Source kitchen fixtures & appliances | Studio Team | 2026-03-20 | 2026-04-10 | 2026-04-08 | Complete | Urgent |  | Range ordered |  |  |  | █ | █
Client Approval | Approve primary suite furniture | Client | 2026-04-01 | 2026-04-15 |  | Waiting on Client | High | Sourcing | [5 empty] | █ | █
Purchasing | Place living room POs | Jordan Blake | 2026-04-01 | 2026-04-12 | 2026-04-10 | Complete | High | Approvals | [5 empty] | █ | █
Construction | Kitchen rough-in coordination | GC | 2026-05-01 | 2026-05-20 |  | Not Started | High | Appliance order | [8 empty] | █ | █
Delivery | Living room furniture delivery | Vendors | 2026-05-15 | 2026-05-25 |  | Not Started | High | POs | [9 empty] | █ | █
Installation | Install living + powder | Installers | 2026-05-20 | 2026-06-05 |  | Not Started | High | Deliveries | [9 empty] | █ | █ | █
Styling | Final styling pass | Jordan Blake | 2026-06-10 | 2026-06-15 |  | Not Started | Medium | Installation | [11 empty] | █ | █
Final Reveal | Client walkthrough | Jordan Blake | 2026-06-18 | 2026-06-18 |  | Not Started | Urgent | Styling | [12 empty] | █
Punch List | Complete punch items | Studio + GC | 2026-06-18 | 2026-06-30 |  | Not Started | High | Reveal | [12 empty] | █

## 16 To-Do List
TASK & TO-DO LIST
Daily working list for the design team · Novality store
Task | Room | Category | Assigned To | Priority | Due Date | Status | Notes
Email client fabric photos for primary bed | Master Bedroom | Client | Jordan Blake | High | 2026-04-12 | In Progress
Confirm Wolf range rough-in dimensions with GC | Kitchen | Site | Studio Team | Urgent | 2026-04-10 | Waiting on Vendor | Need GC response
Order rug pad for living room | Living Room | Purchasing | Studio Team | Medium | 2026-04-15 | Not Started
Schedule elevator for sofa delivery | Living Room | Installation | Jordan Blake | High | 2026-05-10 | Not Started | Building mgmt 48h notice
Update budget actuals after West Elm invoice | — | Admin | Studio Team | Medium | 2026-04-08 | Complete
Request trade quote Four Hands dining chairs | Dining Room | Sourcing | Studio Team | High | 2026-04-14 | In Progress
Send dining table options board to client | Dining Room | Client | Jordan Blake | High | 2026-04-11 | Waiting on Client | Board sent 4/5
Book site visit for powder install | Powder Room | Installation | Studio Team | Medium | 2026-04-20 | Not Started
Collect paint touch-up kit from BM | Living Room | Vendor | Studio Team | Low | 2026-04-30 | Not Started
Review overdue open POs | — | Purchasing | Jordan Blake | Urgent | 2026-04-09 | Delayed | Check Visual Comfort

## 17 Measurements
MEASUREMENT LOG
Field measurements for designers and installers · Novality store
Room | Measurement Type | Width | Height | Depth | Length | Ceiling Height | Window Size | Door Size | Wall Length | Notes
Living Room | Room | 18' | 9' | — | 16' | 9' | — | — | — | Open to dining
Living Room | Window | 6' | 5' | — | — | — | 6' x 5' | — | — | South facing, 2 panels
Living Room | Rug Area | 11' | — | — | 14' | — | — | — | — | Allow 12–18" border
Master Bedroom | Room | 14' | 9' | — | 16' | 9' | — | — | —
Master Bedroom | Furniture Space | 80" | — | 84" | — | — | — | — | — | King bed wall
Kitchen | Room | 12' | 9' | — | 16' | 9' | — | — | — | Island 8' x 3.5'
Kitchen | Cabinet | 36" | 36" | 24" | — | — | — | — | — | Base run east wall
Powder Room | Room | 5' | 9' | — | 8' | 9' | — | 28" door | — | Tight clearances
Home Office | Window | 4' | 5' | — | — | — | 4' x 5' | — | — | Needs treatment
Dining Room | Room | 12' | 9' | — | 14' | 9' | — | — | — | Chandelier center 6' from window wall

## 18 Contractors
CONTRACTOR / INSTALLER TRACKER
Coordinate trades, quotes, insurance, and schedules · Novality store
Contractor/Vendor Name | Trade | Contact | Scope | Quote Amount | Start Date | End Date | Payment Status | Insurance Received | Contract Signed | Notes
Summit Build Co. | General Contractor | Mike Torres · 555-2001 | Kitchen rough-in & coordination | 8500 | 2026-05-01 | 2026-06-15 | Partially Paid | Yes | Yes | COI on file
Lumen Electric | Electrician | Priya Nair · 555-2002 | Island pendants + recessed | 2200 | 2026-05-10 | 2026-05-18 | Unpaid | Yes | Yes
Cascade Plumbing | Plumber | Ed Walsh · 555-2003 | Powder vessel sink install | 980 | 2026-05-01 | 2026-05-03 | Unpaid | Yes | Yes
Oak & Stone Floors | Flooring Installer | Lee Cho · 555-2004 | Living white oak install | 4200 | 2026-04-20 | 2026-04-28 | Paid | Yes | Yes | Completed
Paper & Paste | Wallpaper Installer | Nina Sol · 555-2005 | Powder grasscloth | 750 | 2026-05-05 | 2026-05-06 | Unpaid | Yes | No | Send contract
White Glove Crew | Furniture Installer | Dispatch · 555-2006 | Living room furniture set | 450 | 2026-05-25 | 2026-05-25 | Unpaid | Yes | Yes | Article partner
Fresh Coat Pros | Painter | Tom Rivera · 555-2007 | Touch-ups post install | 600 | 2026-06-10 | 2026-06-12 | Unpaid | No | No | Need COI

## 19 Invoices
INVOICE & PAYMENT TRACKER
Client billing for design fees and reimbursable items · Novality store
Invoice Number | Invoice Date | Client | Description | Amount | Due Date | Paid Date | Payment Status | Payment Method | Notes
INV-2026-01 | 2026-03-01 | Alexandra Chen | Design retainer / deposit | 4000 | 2026-03-15 | 2026-03-10 | Paid | ACH
INV-2026-02 | 2026-04-01 | Alexandra Chen | Concept design milestone | 4000 | 2026-04-15 | 2026-04-12 | Paid | ACH
INV-2026-03 | 2026-05-01 | Alexandra Chen | Procurement milestone | 4000 | 2026-05-15 |  | Sent |  | Due mid-month
INV-2026-04 | 2026-03-25 | Alexandra Chen | Reimbursable: rug + pad | 1378 | 2026-04-08 | 2026-04-05 | Paid | Credit Card
INV-2026-05 | 2026-04-15 | Alexandra Chen | Reimbursable: West Elm chairs | 1460 | 2026-04-30 |  | Sent
INV-2026-06 | 2026-06-01 | Alexandra Chen | Final design fee balance | 0 | 2026-06-15 |  | Draft |  | Calculate at install
TOTALS
Total Paid
Outstanding

## 20 Meeting Notes
PROJECT NOTES / MEETING NOTES
Consultations, vendor meetings, site visits, and walkthroughs · Novality store
Date | Meeting Type | Attendees | Discussion Points | Decisions Made | Action Items | Follow-up Date | Notes
2026-03-01 | Client Consultation | Alexandra Chen, Jordan Blake | Goals, lifestyle, dog-friendly materials, budget $85k | Proceed with full-service FF&E | Send questionnaire; schedule measure | 2026-03-03 | Client loves warm minimalism
2026-03-07 | Site Visit | Jordan Blake, Studio Team | Measured all rooms; noted powder door swing | Use existing oak floors in living | Draft plans; photo log | 2026-03-10 | Good natural light south
2026-03-22 | Client Consultation | Alexandra Chen, Jordan Blake | Concept presentation — boards v2 | Approved palette and living package | Source dining table options | 2026-04-05 | Travel blackout Aug 1–15
2026-04-02 | Vendor Meeting | Jordan Blake, Article Trade | Sofa lead times and white-glove | Order Sven in Stone | Send PO-1001 | 2026-04-03 | Trade 15% applied
2026-04-08 | Contractor Meeting | Mike Torres (GC), Jordan Blake | Kitchen range rough-in & schedule | Rough-in week of May 1 | Confirm gas line size | 2026-04-12 | Need Wolf cut sheet

## 21 Client FF&E Report
CLIENT-FACING FF&E REPORT
Print or PDF this sheet for client presentations · Novality store
Item ID | Room | Category | Item Name | Quantity | Vendor | Finish/Color | Unit Cost | Total | Status
FFE-001 | Living Room | Sofa | Performance Sofa | 1 | Article | Natural oak legs / Stone | 1899 | 1899 | Approved
FFE-002 | Living Room | Chair | Accent Lounge Chair | 2 | West Elm | Black metal / Ivory | 699 | 1398 | Approved
FFE-003 | Living Room | Table | Coffee Table | 1 | CB2 | Brushed brass / White marble | 899 | 899 | Approved
FFE-004 | Living Room | Rug | Area Rug 9x12 | 1 | Loloi | Handwoven / Ivory/Taupe | 1299 | 1299 | Approved
FFE-005 | Living Room | Lighting | Floor Lamp | 1 | Rejuvenation | Antique brass / Brass | 449 | 449 | Approved
FFE-006 | Master Bedroom | Bed | Platform Bed King | 1 | Article | Natural / Oatmeal | 1499 | 1499 | Sent
FFE-007 | Master Bedroom | Lighting | Pendant Pair | 2 | Schoolhouse | Clear glass / Brass | 279 | 558 | Approved
FFE-008 | Kitchen | Appliance | Range 36" | 1 | Wolf | Professional / SS | 8999 | 8999 | Approved
FFE-009 | Kitchen | Lighting | Island Pendants | 3 | Visual Comfort | Aged brass / Brass | 520 | 1560 | Approved
FFE-010 | Dining Room | Table | Dining Table | 1 | Ethnicraft | White oak / Natural | 2499 | 2499 | Not Sent
FFE-011 | Dining Room | Chair | Dining Chairs | 6 | Four Hands | Oak legs / Sand | 349 | 2094 | Not Sent
FFE-012 | Powder Room | Plumbing Fixture | Vessel Sink | 1 | Signature Hardware | Honed / Carrara | 389 | 389 | Approved
FFE-013 | Home Office | Chair | Desk Chair | 1 | Herman Miller | Black / Black | 1395 | 1395 | Not Sent
FFE-014 | Living Room | Artwork | Large Abstract Canvas | 1 | Local Artist | Gallery wrap / Multi | 2200 | 2200 | Sent
FFE-015 | Kitchen | Hardware | Cabinet Pulls | 24 | Rejuvenation | Unlacquered / Brass | 18 | 432 | Approved
TOTAL

## 22 Room Budget Report
ROOM-BY-ROOM BUDGET REPORT
Printable budget summary by area · Novality store
Room | Budget Allocation | Estimated Spend | Actual Spend | Remaining | % Used | Status
TOTAL

## 23 Vendor Order Report
VENDOR ORDER REPORT
Printable open and completed orders by vendor · Novality store
PO Number | Vendor | Item | Qty | Order Date | Status | Amount | Paid Status | Tracking

## 24 Install Checklist
INSTALLATION CHECKLIST
Print for on-site installation day · Novality store
☐ | Item | Room | Vendor | Install Date | Installer | Status | Notes
☑ | Area Rug 9x12 | Living Room | Loloi | 2026-04-11 | Studio Team | Installed
☑ | Floor Lamp | Living Room | Rejuvenation | 2026-04-02 | Studio Team | Installed
☐ | Accent Lounge Chairs | Living Room | West Elm | 2026-05-12 | Studio Team | Scheduled
☐ | Performance Sofa | Living Room | Article | 2026-05-25 | Article White Glove | Not Scheduled | Elevator
☐ | Vessel Sink | Powder Room | Signature Hardware | 2026-05-01 | Plumber | Scheduled
☐ | Island Pendants x3 | Kitchen | Visual Comfort | 2026-05-18 | Electrician | Not Scheduled | After rough-in
☐ | Range 36" | Kitchen | Wolf / Sub-Zero | 2026-06-15 | Appliance Installer | Not Scheduled | Gas check
☐ | Cabinet Pulls | Kitchen | Rejuvenation | 2026-05-20 | GC | Not Scheduled
☐ | Pendant Pair | Master Bedroom | Schoolhouse | 2026-05-22 | Electrician | Not Scheduled

## 25 Punch List
FINAL PUNCH LIST
Print for final walkthrough and close-out · Novality store
☐ | # | Item / Issue | Room | Responsible | Priority | Due Date | Status | Resolution Notes
☐ | 1 | Touch up paint at sofa wall corners | Living Room | Painter | Medium | 2026-06-20 | Not Started
☐ | 2 | Adjust island pendant heights | Kitchen | Electrician | High | 2026-06-18 | Not Started | Client prefers 32" above island
☐ | 3 | Missing felt pads on dining chairs | Dining Room | Studio Team | Low | 2026-06-22 | Not Started
☐ | 4 | Confirm warranty packet delivered | Kitchen | Studio Team | Medium | 2026-06-25 | Not Started | Wolf range docs
☐ | 5 | Replace one damaged cabinet pull | Kitchen | GC | Medium | 2026-06-20 | Not Started | Scratch on finish
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐
☐