## Welcome
INTERIOR DESIGN PROJECT MANAGER
Excel + Google Sheets compatible • Fully editable and unlocked • No macros required
QUICK START GUIDE
| Step 1 | Add client/project details | Complete the Client & Project Profile, including total budget and target dates.
| Step 2 | Add rooms | List each space in Room List. Room names become your standard reference across schedules.
| Step 3 | Add FF&E items | Use Master FF&E for furniture, fixtures and equipment. Add product links, quantities and costs.
| Step 4 | Track execution | Update approvals, orders, delivery, installation, budget and tasks as the project progresses.
| Step 5 | Review the dashboard | Use Project Dashboard for KPIs, risks and visual project summaries.
HOW TO USE THIS WORKBOOK
| Data entry | Enter information in white cells. Blue-tinted cells contain formulas and calculate automatically. Do not paste over formula columns.
| Dropdowns | Click a dropdown cell and choose a standard value. Dropdowns improve dashboard accuracy. Room and vendor dropdowns use the Room List and Vendor Database.
| Color coding | Green = complete/approved/on budget • Yellow = pending/in progress • Red = overdue/over budget/delayed • Gray = cancelled/on hold.
| Filters | Use the arrows in schedule headers to filter by room, vendor, status, approval or date. Clear filters to show all records.
| Compatibility | Designed for Microsoft Excel (.xlsx) and Google Sheets. To use in Sheets: File → Import → Upload. Some chart styling may vary slightly.
| Editable version | This workbook is fully editable and unlocked. Duplicate the original before customizing formulas, colors or tab names.
| Support | Add your business support email, website or product documentation link here before distributing this template.
WHAT EACH TAB IS FOR
Dashboard — project KPIs and charts
Profile / Room List — project setup and space budgets
Master FF&E — central product and cost schedule
Furniture / Fixtures / Finishes — focused specifications
Sourcing / Vendors — compare products and manage suppliers
Budget / Orders / Delivery — purchasing controls
Approvals / Timeline / Tasks — project workflow
Measurements / Contractors / Invoices / Notes — field and admin records
Reports — printable client, budget, vendor and installation views

## Project Dashboard
PROJECT DASHBOARD
Live overview • Complete the Profile, Room List, FF&E, Orders, Approvals and Tasks tabs to populate metrics.
Total Project Budget | Total Estimated Cost | Total Actual Cost | Remaining Budget
0 | 0 | 0 | 0
Budget Used % | Number of Rooms | Total FF&E Items | Items Approved
0% | 0 | 0 | 0
Items Ordered | Items Delivered | Items Installed | Overdue Tasks
0 | 0 | 0 | 0
Pending Client Approvals | Open Vendor Orders | Items Not Ordered | Delivered, Not Installed
0 | 0 | 0 | 0
|  |  |  | Room | Budget | Actual | Budget Category | Budgeted | Actual | Item Status | Count | Delivery Status | Count | Category | Spend
|  |  |  | 0 | 0 | 0 | Furniture | 0 | 0 | Sourcing | 0 | Not scheduled | 0 | Sofa | 0
|  |  |  | 0 | 0 | 0 | Lighting | 0 | 0 | Option selected | 0 | Scheduled | 0 | Chair | 0
|  |  |  | 0 | 0 | 0 | Rugs | 0 | 0 | Client review | 0 | In transit | 0 | Table | 0
|  |  |  | 0 | 0 | 0 | Decor | 0 | 0 | Approved | 0 | Delivered | 0 | Bed | 0
|  |  |  | 0 | 0 | 0 | Artwork | 0 | 0 | Ordered | 0 | Delayed | 0 | Rug | 0
|  |  |  | 0 | 0 | 0 | Window treatments | 0 | 0 | Shipped | 0 | Cancelled | 0 | Lighting | 0
|  |  |  | 0 | 0 | 0 | Flooring | 0 | 0 | Delivered | 0 | Returned | 0 | Artwork | 0
|  |  |  | 0 | 0 | 0 | Paint/wallcovering | 0 | 0 | Installed | 0 |  |  | Mirror | 0
|  |  |  | 0 | 0 | 0 | Contractor labor | 0 | 0 | Cancelled | 0 |  |  | Window treatment | 0
|  |  |  | 0 | 0 | 0 | Installation | 0 | 0 | Backordered | 0 |  |  | Hardware | 0
|  |  |  | 0 | 0 | 0 | Shipping | 0 | 0 |  |  |  |  | Plumbing fixture | 0
|  |  |  | 0 | 0 | 0 | Taxes | 0 | 0 |  |  |  |  | Appliance | 0
|  |  |  | 0 | 0 | 0 | Design fee | 0 | 0 |  |  |  |  | Decor | 0
|  |  |  | 0 | 0 | 0 | Contingency | 0 | 0 |  |  |  |  | Textile | 0
|  |  |  | 0 | 0 | 0 | [7 empty] | Cabinetry | 0
[14 empty] | Flooring | 0
[14 empty] | Wallcovering | 0
[14 empty] | Other | 0

## Client & Project Profile
CLIENT & PROJECT PROFILE
Complete this tab first. Dashboard budget and dates reference these values.
Client name | Scope summary
Client email
Phone number
Project name
Project address
Project type
Design style
Start date
Target completion date | Client notes
Total budget
Designer name
Project status
Contract signed
Deposit paid
Design package selected
Billing method

## Room List
Room List
Use filters in the header row. White cells are inputs; blue cells are formulas.
Room Name | Room Type | Floor / Level | Square Footage | Design Status | Budget Allocation | Estimated Spend | Actual Spend | Remaining Budget | Priority Level | Notes
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0

## Master FF&E
Master FF&E
Furniture, Fixtures & Equipment master schedule. Total Cost = Quantity × Unit Cost; Final Cost = Total + Tax + Shipping − Discount.
Item ID | Room | Category | Item Name | Description | Quantity | Dimensions | Material | Finish | Color | Vendor | Brand | Product Link | SKU / Model Number | Unit Cost | Total Cost | Tax ($) | Shipping ($) | Discount ($) | Final Cost | Lead Time | Order Status | Approval Status | Delivery Status | Install Status | Notes | Image Link
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0
[15 empty] | 0 |  |  |  | 0

## Furniture Schedule
Furniture Schedule
Use filters in the header row. White cells are inputs; blue cells are formulas.
Room | Furniture Item | Dimensions | Quantity | Vendor | Product Link | Fabric / Material | Finish | Cost | Approval Status | Order Status | Delivery Date | Install Date

## Fixtures Schedule
Fixtures Schedule
Use filters in the header row. White cells are inputs; blue cells are formulas.
Room | Fixture Type | Item Name | Finish | Size | Vendor | Model / SKU | Quantity | Unit Cost | Total Cost | Required Rough-in Date | Order Deadline | Delivery Date | Installer Notes
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Finishes Schedule
Finishes Schedule
Use filters in the header row. White cells are inputs; blue cells are formulas.
Room | Surface / Application | Finish Type | Product Name | Color / Finish | Material | Vendor | Product Link | SKU | Quantity Needed | Unit Cost | Total Cost | Sample Ordered | Sample Approved | Installer Notes
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Product Sourcing
Product Sourcing
Use filters in the header row. White cells are inputs; blue cells are formulas.
Room | Item Needed | Option 1 Link | Option 1 Price | Option 2 Link | Option 2 Price | Option 3 Link | Option 3 Price | Preferred Option | Pros | Cons | Client Feedback | Final Selection

## Vendor Database
Vendor Database
Use filters in the header row. White cells are inputs; blue cells are formulas.
Vendor Name | Vendor Type | Contact Person | Email | Phone | Website | Account Number | Trade Discount % | Lead Time | Shipping Terms | Return Policy | Notes

## Budget Tracker
Budget Tracker
Use filters in the header row. White cells are inputs; blue cells are formulas.
Budget Category | Budgeted Amount | Estimated Amount | Actual Amount | Difference | Paid Amount | Balance Due | Payment Status | Notes
Furniture |  |  |  | 0 |  | 0
Lighting |  |  |  | 0 |  | 0
Rugs |  |  |  | 0 |  | 0
Decor |  |  |  | 0 |  | 0
Artwork |  |  |  | 0 |  | 0
Window treatments |  |  |  | 0 |  | 0
Flooring |  |  |  | 0 |  | 0
Paint/wallcovering |  |  |  | 0 |  | 0
Contractor labor |  |  |  | 0 |  | 0
Installation |  |  |  | 0 |  | 0
Shipping |  |  |  | 0 |  | 0
Taxes |  |  |  | 0 |  | 0
Design fee |  |  |  | 0 |  | 0
Contingency |  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
TOTAL | 0 | 0 | 0 | 0 | 0 | 0

## Order Tracker
Order Tracker
Use filters in the header row. White cells are inputs; blue cells are formulas.
PO Number | Vendor | Room | Item | Quantity | Order Date | Expected Ship Date | Expected Delivery Date | Actual Delivery Date | Order Status | Tracking Number | Carrier | Invoice Number | Amount | Paid Status | Notes

## Delivery & Installation
Delivery & Installation
Use filters in the header row. White cells are inputs; blue cells are formulas.
Item | Room | Vendor | Delivery Address | Expected Delivery Date | Actual Delivery Date | Delivery Status | Received By | Damage Check | Damage Notes | Storage Location | Install Date | Installer | Installation Status | Punch List Notes

## Client Approvals
Client Approvals
Use filters in the header row. White cells are inputs; blue cells are formulas.
Item / Design Decision | Room | Approval Type | Sent to Client Date | Client Response Date | Status | Approved Option | Client Comments | Revision Needed | Final Approval Date

## Project Timeline
Project Timeline
Enter task dates, then set the Gantt start date in K2. Weekly bars shade automatically. | [9 empty] | Gantt start: | 0
Phase | Task | Assigned To | Start Date | Due Date | Completion Date | Status | Priority | Dependencies | Notes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Task List
Task List
Use filters in the header row. White cells are inputs; blue cells are formulas.
Task | Room | Category | Assigned To | Priority | Due Date | Status | Notes

## Measurement Log
Measurement Log
Use filters in the header row. White cells are inputs; blue cells are formulas.
Room | Measurement Type | Width | Height | Depth | Length | Ceiling Height | Window Size | Door Size | Wall Length | Notes

## Contractor Tracker
Contractor Tracker
Use filters in the header row. White cells are inputs; blue cells are formulas.
Contractor / Vendor Name | Trade | Contact | Scope | Quote Amount | Start Date | End Date | Payment Status | Insurance Received | Contract Signed | Notes

## Invoice & Payment
Invoice & Payment
Use filters in the header row. White cells are inputs; blue cells are formulas.
Invoice Number | Invoice Date | Client | Description | Amount | Due Date | Paid Date | Payment Status | Payment Method | Notes

## Project Notes
Project Notes
Use filters in the header row. White cells are inputs; blue cells are formulas.
Date | Meeting Type | Attendees | Discussion Points | Decisions Made | Action Items | Follow-up Date | Notes

## Client FF&E Report
CLIENT FF&E SPECIFICATION REPORT
Client-facing live report. Use print settings or filter the Master FF&E tab before sharing.
Item ID | Room | Category | Item | Description | Qty | Dimensions | Material | Finish | Color | Vendor | Brand | Product Link | SKU | Unit Cost | Total | Tax | Shipping | Discount | Final Cost | Lead Time | Order | Approval | Delivery | Install | Notes | Image
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Room Budget Report
ROOM-BY-ROOM BUDGET REPORT
Live summary of room allocations and spend.
Room | Type | Floor | Sq Ft | Status | Budget | Estimated | Actual | Remaining | Priority | Notes
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Vendor Order Report
VENDOR ORDER REPORT
Live purchasing report. Filter the Order Tracker by vendor or status for targeted reports.
PO | Vendor | Room | Item | Qty | Order Date | Expected Ship | Expected Delivery | Actual Delivery | Status | Tracking | Carrier | Invoice | Amount | Paid | Notes
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Installation Checklist
DELIVERY & INSTALLATION CHECKLIST
Print-ready field checklist for receiving and installation days.
Item | Room | Vendor | Address | Expected | Actual | Delivery Status | Received By | Damage Check | Damage Notes | Storage | Install Date | Installer | Install Status | Punch List
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Final Punch List
FINAL PUNCH LIST
Shows records with punch-list notes. Keep this report internal until ready to share.
Item | Room | Vendor | Address | Expected | Actual | Delivery Status | Received By | Damage Check | Damage Notes | Storage | Install Date | Installer | Install Status | Punch List
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Lists (hidden)
RoomTypes | ProjectTypes | ProjectStatuses | BillingMethods | YesNo | Priorities | DesignStatuses | Categories | ApprovalStatuses | OrderStatuses | DeliveryStatuses | InstallStatuses | FixtureTypes | FinishTypes | Surfaces | VendorTypes | BudgetCategories | PaymentStatuses | DamageChecks | ApprovalTypes | ApprovalTrackerStatuses | Phases | TaskStatuses | MeasurementTypes | Trades | InvoiceStatuses | MeetingTypes
Living room | Residential | Not started | Flat fee | Yes | Low | Not started | Sofa | Not sent | Not ordered | Not scheduled | Not ready | Lighting | Paint | Wall | Furniture | Furniture | Not paid | Not checked | Furniture | Not sent | Consultation | Not started | Room | General contractor | Draft | Client consultation
Bedroom | Commercial | Planning | Hourly | No | Medium | Concept | Chair | Sent | Sourcing | Scheduled | Ready to install | Faucet | Wallpaper | Ceiling | Lighting | Lighting | Deposit paid | Good condition | Finish | Sent | Measurements | In progress | Wall | Painter | Sent | Vendor meeting
Kitchen | Office | In progress | Percentage |  | High | Sourcing | Table | Client review | Option selected | In transit | Scheduled | Sink | Flooring | Floor | Fabric | Rugs | Partially paid | Damaged | Layout | Approved | Concept design | Waiting on client | Window | Electrician | Paid | Site visit
Bathroom | Retail | On hold | Hybrid |  | Urgent | Client review | Bed | Approved | Client review | Delivered | Installed | Shower fixture | Tile | Cabinet | Flooring | Decor | Paid | Missing item | Color palette | Revisions requested | Sourcing | Waiting on vendor | Door | Plumber | Partially paid | Installation meeting
Dining room | Hospitality | Complete |  |  |  | Approved | Rug | Revisions requested | Approved | Delayed | Punch list | Tub | Countertop | Countertop | Tile | Artwork | Overdue | Wrong item | Budget | Rejected | Client approval | Complete | Cabinet | Flooring installer | Overdue | Contractor meeting
Entryway | Staging | Cancelled |  |  |  | Ordered | Lighting | Rejected | Ordered | Cancelled | Complete | Toilet | Backsplash | Shower wall | Paint | Window treatments | Cancelled |  | Purchase | On hold | Purchasing | Delayed | Furniture space | Tile installer | Cancelled | Final walkthrough
Office | [5 empty] | Installed | Artwork | On hold | Confirmed | Returned | On hold | Cabinet hardware | Cabinet finish | Backsplash | Wallpaper | Flooring | Draft |  | Vendor |  | Construction |  | Rug area | Wallpaper installer
Nursery | [5 empty] | Complete | Mirror |  | In production |  |  | Door hardware | Fabric | Upholstery | Decor | Paint/wallcovering | Sent |  | Design concept |  | Delivery |  | Lighting location | Carpenter
Outdoor | [5 empty] | On hold | Window treatment |  | Shipped |  |  | Appliance | Trim | Drapery | Hardware | Contractor labor |  |  |  |  | Installation |  |  | Window treatment installer
Commercial space | [6 empty] | Hardware |  | Delivered |  |  | Electrical | Stone | Other | Contractor | Installation |  |  |  |  | Styling |  |  | Furniture installer
Other | [6 empty] | Plumbing fixture |  | Delayed |  |  | Other | Wood |  | Installer | Shipping |  |  |  |  | Final reveal |  |  | Cleaner
[7 empty] | Appliance |  | Cancelled |  |  |  | Metal |  | Workroom | Taxes |  |  |  |  | Punch list |  |  | Other
[7 empty] | Decor |  | Returned |  |  |  | Other |  | Custom furniture | Design fee
[7 empty] | Textile |  | Backordered | [5 empty] | Other | Contingency
Cabinetry
Flooring
Wallcovering
Other